## RiskLog
|  |  | Responsibles |  | Status |  |  | Risk Assessment |  |  |  | Dates |  | Business Logic
Key | Jira | Summary | Reporter | Owner | Status | Problem | Resolution | Impact | Likelihood | Severity | Severity Index | Raised | Resolved | BL.existsInExport | BL.showValues | BL.showInMatrix | BL.impactIndex | BL.likelihoodIndex | BL.coordinates
RISKMGMT-2 | Link | Legal regulations cause project delay | Boris Karl Schlein | Boris Karl Schlein | Avoid | 1 |  | Severe | Almost Certain | Critical | 5 | 2022-02-02 |  | 1 | TRUE | 1 | 5 | 5 | i5l5
RISKMGMT-5 | Link | Project purpose is not defined | Boris Karl Schlein |  | Avoid | 1 |  | Moderate | Almost Certain | High | 4 | 2022-02-02 |  | 1 | TRUE | 1 | 3 | 5 | i3l5
RISKMGMT-9 | Link | Example Risk 04 | Boris Karl Schlein |  | Accept | 0 |  | Significant | Almost Certain | High | 4 | 2023-02-16 |  | 1 | TRUE | 1 | 4 | 5 | i4l5
RISKMGMT-3 | Link | Extreme weather causes delay of deliveries (Acts of God) | Boris Karl Schlein | Boris Karl Schlein | Accept | 0 |  | Significant | Unlikely | Medium | 3 | 2022-02-02 |  | 1 | TRUE | 1 | 4 | 2 | i4l2
RISKMGMT-7 | Link | Example Risk 02 | Boris Karl Schlein |  | Accept | 0 |  | Moderate | Possible | Medium | 3 | 2023-02-16 |  | 1 | TRUE | 1 | 3 | 3 | i3l3
RISKMGMT-13 | Link | Example Risk 09 | Boris Karl Schlein |  | Accept | 0 |  | Minor | Likely | Medium | 3 | 2023-02-17 |  | 1 | TRUE | 1 | 2 | 4 | i2l4
RISKMGMT-15 | Link | Example Risk 11 | Boris Karl Schlein |  | Avoid | 0 |  | Significant | Unlikely | Medium | 3 | 2023-02-17 |  | 1 | TRUE | 1 | 4 | 2 | i4l2
RISKMGMT-8 | Link | Example Risk 03 | Boris Karl Schlein |  | Transfer | 0 |  | Significant | Rare | Low | 2 | 2023-02-16 |  | 1 | TRUE | 1 | 4 | 1 | i4l1
RISKMGMT-1 | Link | Lack of communication causing confusion | Boris Karl Schlein |  | Mitigate | 0 |  | Minor | Possible | Low | 2 | 2022-02-02 |  | 1 | TRUE | 1 | 2 | 3 | i2l3
RISKMGMT-6 | Link | Example Risk 01 | Boris Karl Schlein |  | In Clarification | 0 |  | Minor | Possible | Low | 2 | 2023-02-16 |  | 1 | TRUE | 1 | 2 | 3 | i2l3
RISKMGMT-10 | Link | Example Risk 05 | Boris Karl Schlein |  | Mitigate | 0 |  | Moderate | Rare | Low | 2 | 2023-02-16 |  | 1 | TRUE | 1 | 3 | 1 | i3l1
RISKMGMT-12 | Link | Example Risk 08 | Boris Karl Schlein |  | Mitigate | 0 |  | Moderate | Unlikely | Low | 2 | 2023-02-16 |  | 1 | TRUE | 1 | 3 | 2 | i3l2
RISKMGMT-11 | Link | Example Risk 06 | Boris Karl Schlein |  | Transfer | 0 |  | Minor | Rare | Negligible | 1 | 2023-02-16 |  | 1 | TRUE | 1 | 2 | 1 | i2l1
RISKMGMT-14 | Link | Example Risk 10 | Boris Karl Schlein |  | New | 0 |  | Unspecified | Unspecified | Unspecified | 0 | 2023-02-17 |  | 1 | TRUE | 1 | 0 | 0 | i0l0
RISKMGMT-4 | Link | Project goals not defined | Boris Karl Schlein | Boris Karl Schlein | Resolved | 0 | Done | Significant | Possible | Medium | 3 | 2022-02-02 | 2022-02-02 | 1 | TRUE | 0 | 4 | 3 | i4l3
Formulas:
Raised = IF(TBL_RiskLog[[#This Row],[BL.showValues]],XLOOKUP(TBL_RiskLog[[#This Row],[Key]],EXP_Risks[issueKey],EXP_Risks[Created]),"")
Resolved = IF(TBL_RiskLog[[#This Row],[BL.showValues]],IFERROR(IF(ISBLANK(XLOOKUP(TBL_RiskLog[[#This Row],[Key]],EXP_Risks[issueKey],EXP_Risks[Resolved])),"",XLOOKUP(TBL_RiskLog[[#This Row],[Key]],EXP_Risks[issueKey],EXP_Risks[Resolved])),""),"")

## RiskMatrix
Impact | Severe | 5 | 0 | 0 | 0 | 0 | 0 | 1 | Severity Index
| Significant | 4 | 0 | 1 | 2 | 0 | 0 | 1 | Unspecified | Negligible | Low | Medium | High | Critical
| Moderate | 3 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 5 | 4 | 2 | 1
| Minor | 2 | 0 | 1 | 0 | 2 | 1 | 0
| Insignificant | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Unspecified | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 1 | 2 | 3 | 4 | 5
|  |  | Unspecified | Rare | Unlikely | Possible | Likely | Almost Certain
Likelihood

## RiskHistory
Date | Unspecified | Very Low | Low | Medium | High | Critical | Total
2021-10-01 | 3 | 2 | 3 | 4 | 5 | 1 | 18
2021-11-01 | 1 | 1 | 3 | 8 | 3 | 1 | 17
2021-12-01 | 0 | 2 | 5 | 6 | 2 | 0 | 15
2022-01-01 | 0 | 3 | 4 | 6 | 1 | 0 | 14
2022-02-01 | 0 | 2 | 5 | 4 | 2 | 1 | 14
2022-03-01 | 1 | 1 | 5 | 4 | 2 | 1 | 14

## Export
issueKey | issueID | issueType | Reporter | Reporter ID | Assignee | Assignee ID | Summary | Status | Resolution | Priority | Created | Resolved | Flagged | Labels | field::impact | field::likelihood | BL.existsInRiskLog
RISKMGMT-1 | 10156 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Lack of communication causing confusion | Mitigate |  | Unspecified | 2022-02-02 |  | False |  | Minor | Possible | 1
RISKMGMT-2 | 10157 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea | Legal regulations cause project delay | Avoid |  | High | 2022-02-02 |  | True |  | Severe | Almost Certain | 1
RISKMGMT-3 | 10158 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea | Extreme weather causes delay of deliveries (Acts of God) | Accept |  | High | 2022-02-02 |  | False |  | Significant | Unlikely | 1
RISKMGMT-4 | 10159 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea | Project goals not defined | Resolved | Done | High | 2022-02-02 | 2022-02-02 | False |  | Significant | Possible | 1
RISKMGMT-5 | 10160 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Project purpose is not defined | Avoid |  | High | 2022-02-02 |  | True |  | Moderate | Almost Certain | 1
RISKMGMT-6 | 10275 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 01 | In Clarification |  | Medium | 2023-02-16 |  | False |  | Minor | Possible | 1
RISKMGMT-7 | 10276 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 02 | Accept |  | Medium | 2023-02-16 |  | False |  | Moderate | Possible | 1
RISKMGMT-8 | 10277 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 03 | Transfer |  | Medium | 2023-02-16 |  | False |  | Significant | Rare | 1
RISKMGMT-9 | 10278 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 04 | Accept |  | Medium | 2023-02-16 |  | False |  | Significant | Almost Certain | 1
RISKMGMT-10 | 10279 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 05 | Mitigate |  | Medium | 2023-02-16 |  | False |  | Moderate | Rare | 1
RISKMGMT-11 | 10280 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 06 | Transfer |  | Medium | 2023-02-16 |  | False |  | Minor | Rare | 1
RISKMGMT-12 | 10281 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 08 | Mitigate |  | Medium | 2023-02-16 |  | False |  | Moderate | Unlikely | 1
RISKMGMT-13 | 10282 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 09 | Accept |  | Medium | 2023-02-17 |  | False |  | Minor | Likely | 1
RISKMGMT-14 | 10283 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 10 | New |  | Medium | 2023-02-17 |  | False |  | Unspecified | Unspecified | 1
RISKMGMT-15 | 10284 | Risk | Boris Karl Schlein | 5jekl30lrms0b8e2b9bc0c1ea |  |  | Example Risk 11 | Avoid |  | Medium | 2023-02-17 |  | False |  | Significant | Unlikely | 1

## Logic (hidden)
Number of Missing Items
Risk Log: | 0
Export: | 0
Error Message:

## MasterData
Likelihood |  |  |  | Constants
Name | Order | Description |  | Project Key | RISKMGMT
Unspecified | 0 |  |  | Base URL | https://[your-name].atlassian.net
Rare | 1
Unlikely | 2
Possible | 3
Likely | 4
Almost Certain | 5
Impact
Name | Order | Description
Unspecified | 0
Insignificant | 1
Minor | 2
Moderate | 3
Significant | 4
Severe | 5
Severity
Name | Order | Description
Unspecified | 0
Negligible | 1
Low | 2
Medium | 3
High | 4
Critical | 5
Status
Name | Order | Description
New | 0
In Clarification | 1
Avoid | 2
Mitigate | 3
Transfer | 4
Accept | 5
Resolved | 6
Archived | 7
Resolution Mapping
Name | Order | Mapping
Unresolved | 0 | Unresolved
Done | 1 | Done
Fixed | 2 | Done
Resuolutions
Name | Order | Description
Unresolved | 0
Done | 1
Rejected | 2
Risk Strategies
Name | Order | Description
Avoid | 1
Mitigate | 2
Transfer | 3
Accept | 4
Severity Mapping
Coordinates | Impact | Likelihood | Severity
i0l0 | 0 | 0 | Unspecified
i0l1 | 0 | 1 | Negligible
i0l2 | 0 | 2 | Negligible
i0l3 | 0 | 3 | Low
i0l4 | 0 | 4 | Low
i0l5 | 0 | 5 | Low
i1l0 | 1 | 0 | Negligible
i1l1 | 1 | 1 | Negligible
i1l2 | 1 | 2 | Negligible
i1l3 | 1 | 3 | Low
i1l4 | 1 | 4 | Low
i1l5 | 1 | 5 | Low
i2l0 | 2 | 0 | Negligible
i2l1 | 2 | 1 | Negligible
i2l2 | 2 | 2 | Low
i2l3 | 2 | 3 | Low
i2l4 | 2 | 4 | Medium
i2l5 | 2 | 5 | Medium
i3l0 | 3 | 0 | Low
i3l1 | 3 | 1 | Low
i3l2 | 3 | 2 | Low
i3l3 | 3 | 3 | Medium
i3l4 | 3 | 4 | Medium
i3l5 | 3 | 5 | High
i4l0 | 4 | 0 | Low
i4l1 | 4 | 1 | Low
i4l2 | 4 | 2 | Medium
i4l3 | 4 | 3 | Medium
i4l4 | 4 | 4 | High
i4l5 | 4 | 5 | High
i5l0 | 5 | 0 | Low
i5l1 | 5 | 1 | Low
i5l2 | 5 | 2 | Medium
i5l3 | 5 | 3 | High
i5l4 | 5 | 4 | High
i5l5 | 5 | 5 | Critical

## GeneralInfo
This work is licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License (http://creativecommons.org/licenses/by-nc-sa/4.0/).
About this MS Excel file
I created this Excel workbook over the years, refined it, and finally decided to publish it on GitHub (https://github.com/bks07/risk-log) and write a Medium article to share it with others. You can find the article "Easy Risk Management with Jira" at ... There, you can find everything you need to work with this file.
About me
I am Boris Karl Schlein. You may contact me via LinkedIn at https://www.linkedin.com/in/boriskarlschlein/.
Find me on Medium at https://medium.com/@boris-karl-schlein and on GitHub at https://github.com/bks07.
Versioning (YYYY-MM-DD #XXX <AUTHOR>)
2022-02-11 #001 Boris Karl Schlein
2023-03-01 #002 Boris Karl Schlein
2024-03-12 #003 Boris Karl Schlein (VLOOKUP -> XLOOKUP)